## Sheet1
Risk | Outcome | Responsibility | Impact | Likelihood | Risk Factor | Control/Mitigation | Response | New Impact | New Likelihood | New Risk Factor
Customer Details Breached | Damage to users company reputation | Developer | 4 | 3 | 12 | Encript data | Inform customers instantly. Prevent more customers from using site until breach issue is resolved. Resolve Problem. | 4 | 1 | 4
SQL Injection | Damage to users company reputation | Developer | 5 | 3 | 15 | Ensure SQL packages are up to date | Inform customers instantly. Prevent more customers from using site until breach issue is resolved. Resolve Problem. | 4 | 1 | 4
Going over the project deadline | Customer software rollout delayed. Damage to developer reputation. | Developer | 3 | 2 | 6 | Ensure project plan is followed closely. Employ AGILE into work ethic. | Inform users that that project will be delayed and give an accurate estimate of new deadline date. | 2 | 1 | 2
Code not functioning | Customer software rollout delayed. Damage to developer reputation. | Developer | 3 | 3 | 9 | Ensure project plan is followed closely. Employ AGILE into work ethic. This thus giving the developer enough time to work through each section of code ensuring everything is in working order. | Inform users that that project will be delayed and give an accurate estimate of new deadline date. | 2 | 1 | 2
Customer gives incorrect details to user | User will not be able to create new orders for the customer etc. as they may not be found int the system with their correct details. | Cusomer | 3 | 2 | 6 | User must promt customer to ensure details being entered are correct. | User must create new account for the customer OR user must manually search for previosuly incorrectly entered details. | 3 | 1 | 3
User enters incorrect details for customer | User will not be able to create new orders for the customer etc. as they may not be found int the system with their correct details. | User | 3 | 3 | 9 | User must confirm with customer that details being entered are correct. | User must create new account for the customer OR user must manually search for previosuly incorrectly entered details. | 3 | 2 | 6
User enters incorrect details for item | User will not be able to create new orders for the customer etc. as specific items may not be found int the system with their correct details. | User | 3 | 3 | 9 | User must confirm with customer that item details being entered are correct. | User must offer alternative similar product to customer OR user must manually search for item with previosuly incorrectly entered details. | 3 | 2 | 6